## Project Plan
CEO Recruitment and Onboarding - Project Plan
# |  | Action | Action Owner | Dependency | Due Date | Status | Notes
1 | Overall Planning & Sign off process
| 1.1 | Agree phased approach & timing for project |  |  |  | Not Started
| 1.2 | Executive Director job description approval |  |  |  | Not Started
| 1.3 | Compensation - Market review |  |  |  | Not Started
| 1.4 | Secure budget |  |  |  | Not Started
| 1.5 | Budget for Relocation? |  |  |  | Not Started
| 1.6 | Governance Committee Review / Approval |  |  |  | Not Started
| 1.7 | Board of Trustees Review / Approval |  |  |  | Not Started
2 | Pre Recruitment
| 2.1 | Job Description design (Role summary, Essential Functions & expectations, requirements) |  |  |  | Not Started
| 2.2 | Resume and Application collection process (recommending google forms) |  |  |  | Not Started
| 2.3 | Create knock out and PreScreen Questions |  |  |  | Not Started
| 2.4 | JD Review and Approval by Governance Committee |  |  |  | Not Started
| 2.5 | JD Review and Approval by BOT |  |  |  | Not Started
| 2.6 | Public Search - FAQs & PR Statement |  |  |  | Not Started
3 | Posting / Advertisting Position
| 3.1 | List of all posting sites on ED Search folder and review with Board of Trustees |  | 2.1 |  | Not Started
| 3.2 | Board Source |  | 3.1 |  | Not Started
| 6.3 | https://philanthropynewsdigest.org/ (Candid/ GuideStar) |  | 3.1 |  | Not Started
| 6.4 | Company Facebook Site |  | 3.1 |  | Not Started
| 6.5 | Company LinkedIn Site |  | 3.1 |  | Not Started
| 6.6 | Newspaper advertising? |  | 3.1 |  | Not Started
| 6.7 | Retained agency search (recommend waiting) |  | 3.1 |  | Not Started
| 6.8 | Direct outreach |  | 3.1 |  | Not Started
| 6.9 | BOT and Staff members cascade and share on personal sites |  | 3.1 |  | Not Started
4 | Recruitment
| 4.1 | Applications and Resumes landing site management |  |  |  | Not Started
| 4.2 | Assess applications against Basic Qualifications |  |  |  | Not Started
| 4.3 | Applicant outreach emaisl to schedule phone interviews leading candidates |  |  |  | Not Started
| 4.4 | Applicant rejection emails for those not qualified |  |  |  | Not Started
5 | Interivew Process
| 5.1 | First reviewer of all resumes |  |  |  | Not Started
| 5.2 | Second reviewer broken down by Taskforce members |  |  |  | Not Started
| 5.3 | Phone Interviews for leading candidates who meet all qualifications (Round 1) |  |  |  | Not Started
| 5.4 | Interview guide and Lead for Zoom panel interviews |  |  |  | Not Started
| 5.5 | Interview refresher guide |  |  |  | Not Started
| 5.6 | Zoom panel interview scheduler post phone screen |  |  |  | Not Started
| 5.7 | Interview Panel Team sign up schedule (Round 2) |  |  |  | Not Started
| 5.8 | Interview notes structure and process |  |  |  | Not Started
| 5.9 | BOT and key staff members interview (Round 3) |  |  |  | Not Started
6 | Selection Process
| 6.1 | Recruitment team review all viable candidates to top 3 candidates |  |  |  | Not Started
| 6.2 | Special BOT meeting for review and vote on the top 3 candidates |  |  |  | Not Started
| 6.3 | Offer extension (verbal, accepted, written, accepted) |  |  |  | Not Started
| 6.4 | Post offer acceptance background check |  |  |  | Not Started
| 6.5 | *Adverse impact and rescind letters if needed* |  |  |  | Not Started
7 | Pre Onboarding
| 7.1 | New Hire Paperwork - Payroll and Benefit enrollment forms |  |  |  | Not Started
| 7.2 | Employee Handbook Acknowledgement |  |  |  | Not Started
| 7.3 | I-9 |  |  |  | Not Started
| 7.4 | Pre-Onboarding checklist for set ups |  |  |  | Not Started
8 | Onboarding
| 8.1 | New Employee profile created in Payroll |  |  |  | Not Started
| 8.2 | New employee profile created in Benefits |  |  |  | Not Started
| 8.3 | Employee file created |  |  |  | Not Started
| 8.4 | Employee checklist confirmation |  |  |  | Not Started
| 8.5 | IT creates system identity and security |  |  |  | Not Started
| 8.6 | IT orders phone/ computer |  |  |  | Not Started
9 | Orientation and Training
| 9.1 | Company Orientation |  |  |  | Not Started
| 9.2 | Training |  |  |  | Not Started
| 9.3 | Meet & Greets - Staff, Sites, Board Members |  |  |  | Not Started
| 9.4 | Transition |  |  |  | Not Started
10 | Communication
| 10.1 | Staff |  | 6.3 |  | Not Started
| 10.2 | Clients /Parents |  | 6.3 |  | Not Started
| 10.3 | Vendors |  | 6.3 |  | Not Started
| 10.4 | Press Release |  | 6.3 |  | Not Started
| 10.5 | Donors |  | 6.3 |  | Not Started